## Log
Item | Pri | Description | By | Dept | Date | Resp | Company | Due Date | Status | Status Notes
1 |  | Client has asked us to revise temp sensor range from 20-40C to 10-18C to be more representative to the range measured | LR | Client | 2024-10-10 | JM | Sensors | 2024-10-24 | Canceled | 241017 Per client meeting on Oct. 20, client decided to keep range the same as it provided a more accurate reading for the sensor selected
2 |  | Revise cansat orientation | LR | Client | 2024-10-17 | AK | Sensors | 2024-11-11 | Hold | 241017 Per client meetings on Oct 16, task on hold until results of sensor testing
3 | 1 | Revise Board | AK | Sensors | 2024-11-06 | LR | Client | 2024-11-11 | In progress | 241020 No updates, will issue Change Order next week if no update as delay will impact project schedule 241018 Parts delayed until 20th 241016 Waiting for parts
4 |  | Revise communication module | LR | Client | 2024-11-06 | LB | Comms | 2024-11-11 | In progress | 241020 Waiting for vendor to confirm communications spec
5 |  | Send product specs | LR | Client | 2024-11-06 | AK | Sensors | 2024-11-11 | complete | 241109 Info sent to LR via email
1 |  | Client has asked us to revise air sensor range to 120kPa | LR | Client | 2024-11-09 | AK | Sensors | 2024-11-11 | Not Started | 241109 Info needed from sensors team to confirm sensor viability. LB to review internally and send
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Last line of calculations

## Notes
Notes | Purpose of sheet
Complete list before project kick-off meeting | Identify tasks
Do not delete items, only cancel and filter out | Define group priorities
Focus on project priority ones | Communicate
Only one person controls the sheet | Track
One task per item
Priority 1 is anything that will impact cost or schedule
Track all decisions
Rename file each day so that you have the latest version plus backups
If additional room required, insert lines above the LAST LINE OF CALCS line - this will keep the formatting
Status
Not Started
In Progress
Complete
Hold
Canceled
CTW - completed this week. Rename to Complete after project meeting
Status Notes
example - 240625 - Provided info to Jan
YYMMDD
Alt Enter - for next line in update